## Project Estimation
Ztech Dental Lab — Project Estimation
Next.js + Supabase ¦ Build from scratch
# | Feature | Description | Estimate (hours)
Setup & Infrastructure
1 | Project Setup | Next.js, Supabase, shadcn/ui, folder structure | 2
2 | Database Design | Tables for users, cases, uploads, labs, doctors | 3
3 | Deployment | Hosting, domain, environment config | 1
Subtotal — Setup & Infrastructure |  |  | 6
Authentication
4 | Login Page | Email & password login with Supabase Auth | 1
5 | Session & Access Control | Protect pages, redirect if not logged in | 1
Subtotal — Authentication |  |  | 2
Dashboard
6 | KPI Summary Cards | 7 cards: revenue, cases, labs, doctors, statuses | 1
7 | Revenue Trend Chart | Area chart — revenue over time (daily/weekly/monthly) | 1
8 | Customer Trend Chart | Multi-line chart — labs, doctors, patients over time | 1
9 | Volume Trend Chart | Stacked bar chart by case status | 1
10 | Product Category Chart | Horizontal bar chart — top 10 categories | 1
11 | Top Labs & Doctors | Two ranked tables with name, cases, revenue | 1
12 | Client Activity Heatmap | Interactive heatmap with date filter, sort, tooltips | 4
Subtotal — Dashboard |  |  | 10
Data Upload
13 | Upload History Table | File list with status, date, uploader, pagination | 1
14 | File Upload Dialog | Drag & drop upload for Excel files | 2
15 | Excel Data Processing | Parse uploaded files and save to Supabase | 3
Subtotal — Data Upload |  |  | 6
User Management
16 | User List | Table with name, email, created date, pagination | 2
17 | Add / Edit / Delete | Create, update, remove user accounts | 2
Subtotal — User Management |  |  | 4
Quality & Launch
18 | Testing & Bug Fixes | Test all features, fix issues, edge cases | 3
19 | Review & Go Live | Customer walkthrough, feedback, final adjustments | 2
Subtotal — Quality & Launch |  |  | 5
TOTAL |  |  | 33h